## Sprint 2 Backlog
|  |  | Points Remaining |  | Points Completed
Story | Tasks | Points |  | Assignee | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Complete
Sort list of procedures | By distance in radius | 1 | 0 | Lachlan |  | 1 |  |  |  | Yes
| GUI for setting radius | 1 | 0 | Lachlan |  | 1 |  |  |  | Yes
View Map | Find a suitable API | 1 | 0 | Nicole |  |  | 1 |  |  | Yes
| Refine integration | 4 | 1 | Cameron |  |  | 1 | 2 |  | No
| Display map on GUI | 3 | 0 | Nicole/Cameron |  | 1 | 2 |  |  | Yes
| Place a pin on the map at live location | 2 | 1 | Nicole |  | 1 |  |  |  | No
| Display radius on map around the live location | 4 | 0 | Nicole |  |  | 2 | 2 |  | Yes
| Choose radius to find locations in | 1 | 1 | Lachlan | [5 empty] | No
Click on pins to gain more information | Create GUI output | 3 | 0 | lachlan/steven |  |  | 2 | 1 |  | Yes
| Click on a pin | 3 | 2 | Nicole |  |  | 1 |  |  | No
| Retrieve information from database | 1 | 0 | Cameron |  |  |  | 1 |  | Yes
| Retrieve information from pin | 2 | 1 | Nicole |  |  | 1 |  |  | No
Create GUI | Button triggers search for hospitals | 2 | 0 | Steven/Cai |  |  |  | 2 |  | Yes
| Find design on boostrap | 4 | 2 | Lachlan |  | 2 |  |  |  | No
| Implement into current design | 2 | 0 | Lachlan |  |  | 1 | 1 |  | Yes
User can access website | Implement search restriction controls | 5 | 5 | Lachlan | [5 empty] | No
| Implement map viewer | 2 | 0 | Cameron/Nicole |  |  | 1 | 1 |  | Yes
| Make map viewable on jsp website | 2 | 0 | Lachlan/Nicole |  |  |  | 2 |  | Yes
| Implement list output | 2 | 0 | Cameron |  |  |  | 2 |  | Yes
| Host the website | 2 | 2 | Andrew | [5 empty] | No
| Create database connection | 2 | 2 | Cameron | [5 empty] | No

## Team Roster
Name | Matriculation Number | Email Address
Cameron McNeill | 170014393 | cxmcneill@dundee.ac.uk
Steven Marshall | 170008935 | stevenm682@gmail.com
Lachlan Dow | 170010225 | lxdow@dundee.ac.uk
Nicole Orr | 170010591 | nmorr@dundee.ac.uk
Andrew Holligan | 170014201 | ajholligan@dundee.ac.uk
Cai Jingfan | 2396229 | 2396229@dundee.ac.uk

## Analytics
Total Points for Sprint
49 |  |  |  | 0
Points Remaining
Day 1 | Day 2 | Day 3 | Day 4 | Day 5
49 | 43 | 31 | 17 | 17