## Sheet1
Story Description | Priority | Complexity | ROI | Status
As a user I want to view a list of options/procedures | 10 | 4 | 2.5 | Complete
As a Developer I want to design a GUI for all screens | 10 | 2 | 5 | Complete
As a user I want to search for a procedure | 9 | 3 | 3 | Complete
As a user I want to search for a procedure using its procedure code | 9 | 1 | 9 | Complete
As a user I want to sort the list of procedures by distance | 8 | 1 | 8 | Active
As a user I want to restrict search based on price range | 7 | 1 | 7 | Active
As a Developer I want to research how to add pins to a map so I can develop further functionality for the user interface | 6 | 8 | 0.75 | Active
As a Developer I want to reasearch how to calculate distance between 2 sets of co-ordinates so I can display more useful information | 6 | 8 | 0.75 | Active
As a Developer I want to reasearch how to display maps | 6 | 8 | 0.75 | Active
As a Developer I want to research live location so I can make the map more relative to the user | 6 | 8 | 0.75 | Active
As a user I want to sort the list of procedures based on the distance from live location | 5 | 3 | 1.66
As a user I want to restrict search based on distance range | 5 | 4 | 1.25
As a user I want to view a map with pins displaying location of procedures | 4 | 8 | 0.5
As an admin I want to log into the crud page | 3 | 2 | 1.5 | Active
As an admin I want to add new data to the dataset | 2 | 2 | 1 | Active
As an admin I want to delete existing data in the data set | 2 | 1 | 2 | Active
As an admin I want to update existing data in the dataset | 1 | 2 | 0.5 | Active
As a user I want to click on a pin on a map so I can see data for that location | 5 | 2 |  | Active
As a Developer I want to research choosing a radius on a map | 6 | 2 |  | Active