## Sprint 2 Backlog
|  |  | Points Remaining |  | Points Completed
Story | Tasks | Points |  | Assignee | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Complete
Sort list of procedures | By distance in radius | 1 | 0 | Lchlano |  | 1 |  |  |  | Yes
| GUI for setting radius | 1 | 0 | Lchlano |  | 1 |  |  |  | Yes
View Map | Find a suitable API | 1 | 1 | cam | [5 empty] | No
| Refine integration | 4 | 4 | [6 empty] | No
| Display map on GUI | 7 | 7 | [6 empty] | No
| Place a pin on the map at current location | 1 | 1 | [6 empty] | No
| Display radius on map around the live location | 4 | 4 | n | [5 empty] | No
| Choose radius to find locations in | 1 | 1 | [6 empty] | No
Click on pins to gain more information | Create GUI output | 3 | 3 | Stevn | [5 empty] | No
| Click on a pin | 3 | 3 | [6 empty] | No
| Retrieve information from database | 1 | 1 | [6 empty] | No
| Retrieve information from pin | 2 | 2 | [6 empty] | No
Create GUI | Find design on boostrap | 2 | 0 | Lachlan |  | 2 |  |  |  | Yes
User can access website | Implement search restriction controls | 5 | 5 | [6 empty] | No
| Implement map viewer | 2 | 2 | [6 empty] | No
| Implement list output | 2 | 2 | [6 empty] | No
| Host the website | 2 | 2 | [6 empty] | No
| Create database connection | 2 | 2 | [6 empty] | No

## Analytics
Total Points for Sprint
44 |  |  |  | 0
Day 1 | Day 2 | Day 3 | Day 4 | Day 5
44 | 40 | 40 | 40 | 40